## 1·Exec Dashboard
PMOS™ RECOVERY COMMAND CENTER
Executive Dashboard · live program health, recovery progress & financial exposure · figures auto-calculated from all tabs
| Program | Project Atlas — SAP S/4HANA |  |  |  | Report date | 2026-06-20
| Program Manager | K. Rawat |  |  |  | Go-live target | 2026-09-30
PROGRAM HEALTH AT A GLANCE
| PMOS HEALTH (0–100) |  | RECOVERY SCORE |  |  | GO-LIVE READINESS
| 25 |  | 37.14% |  |  | 45.33%
| FINANCIAL EXPOSURE |  | OPEN CRITICAL RISKS |  |  | OVERDUE DECISIONS
| 7900254.0416 |  | 2 |  |  | 0
KPI TREND — LAST 4 WEEKS
| KPI | W-3 | W-2 | W-1 | Now | Trend
| PMOS Health | 18 | 24 | 26 | 25 | ▼ dn
| Open Risks | 14 | 12 | 11 | 3 | ▼ dn
| Open Decisions | 9 | 8 | 6 | 3 | ▼ dn
| Recovery % | 10 | 18 | 25 | 37 | ▲ up
| Conventions | Blue = your inputs · Black = formulas · Green = links from other tabs. Update blue cells; everything else recalculates.

## ★ Project Atlas (example)
PROJECT ATLAS — A REAL ERP RECOVERY, START TO FINISH
This worked example shows how an experienced recovery lead used the Command Center across 90 days. Names are anonymised; the pattern is real. Read it as 'what a consultant would actually do' — then apply the same moves to your own program in the other tabs.
WEEK 0 — THE SITUATION WE INHERITED
Atlas is a $15M SAP S/4HANA finance & supply-chain transformation, 11 weeks from a hard go-live tied to a fiscal year-end. On paper: RAG amber, 78% 'complete'. In reality: the date was going to be missed and nobody had said so out loud.
The PMOS diagnostic scored the program at composite health 21/100 — bottom quartile. Four of the five behavioral patterns were critical or elevated. This is what those scores meant in practice:
STARTING BEHAVIORAL STATE (Week 0)
Pattern | Score | What it looked like on Atlas
Hero Dependency™ | 95 | Two consultants held all the middleware and pricing-config knowledge. Neither had taken leave in 4 months.
Death By Governance™ | 88 | Six standing forums. A change took 4 sign-offs and 3 weeks to clear.
Nobody Wants To Decide™ | 85 | The chart-of-accounts decision had been 're-discussed' in 7 meetings across 6 weeks.
Silent Resistance™ | 70 | Finance still ran a parallel spreadsheet 'just in case'. Adoption was theatre.
Builder Culture™ | 30 | Problems were escalated, not solved. The team waited to be told.
WHAT THE RECOVERY LEAD ACTUALLY DID (the first move matters most)
Week 1 | Did NOT build a new plan. Opened the RAID and Decision tabs and made the invisible visible: 14 open risks, 9 stuck decisions, one of them blocking cutover. Booked a 45-minute sponsor session — not a status update, a contracting conversation.
Week 1 | Killed one of the six forums on the spot. Publicly. It had produced no decision in a month. This single act signalled that the recovery was real and reclaimed ~8 person-days a week.
Week 2 | Mapped the hero load. Named a backup for each single-point-of-failure consultant and started a runbook. The bus-factor risk (R2) moved from 'invisible' to 'being actively closed'.
Week 2 | Put one named owner and a deadline on every open decision. The chart-of-accounts decision that had circulated for 6 weeks was closed in 4 days once a single person owned it.
Week 4 | Ran the first mock cutover. It failed — which was the point. Better to fail a rehearsal in week 4 than the real thing on go-live night. Eleven gaps logged and owned.
Week 6-8 | Converted two resistant finance leads by giving them a visible quick win, not a training session. The parallel spreadsheet started to disappear on its own.
WHERE ATLAS LANDED (Day 90)
Measure | Week 0 | Day 30 | Day 60 | Day 90
PMOS composite health | 21 | 34 | 58 | 79
Open critical risks | 9 | 8 | 4 | 2
Stuck decisions | 9 | 5 | 2 | 0
Go-live readiness | 31% | 45% | 68% | 88%
Hero Dependency score | 95 | 80 | 55 | 40
Adoption (finance) | 35% | 42% | 61% | 84%
THE LESSON
Atlas did not recover because someone wrote a better plan. It recovered because the recovery lead made the behavioral problems visible, put single owners on decisions, broke the hero dependency, and killed governance that cost more than it protected — in that order, in the first two weeks. The Command Center is the instrument that made each of those moves trackable. Go-live happened 3 weeks later than the original date, on a date the business chose deliberately — not one it was forced into.
Your turn: the other tabs are pre-loaded with Atlas data so you can see a live example. Clear them and enter your own program, or use Atlas as the template for the moves that work.

## 2·RAID Register
RAID REGISTER
Risks · Assumptions · Issues · Dependencies — Priority auto-calculates from Likelihood × Impact. Worked examples shown; replace with your own.
| How to use | One row per item. Set Type, Likelihood, Impact via the dropdowns — Priority colours automatically. Filter by clicking the header row.
| ID | Type | Description | Likelihood | Impact | Priority | Status | Owner | Mitigation / Action | Due | PMOS Pattern | rank
| R1 | Risk | Data migration: legacy vendor master has 18% duplicate records; cleansing not started | High | Critical | Critical | Open | Data Lead | Stand up cleansing squad; freeze new vendor creation | 2026-07-15 | Silent Resistance | 1
| R2 | Risk | Only one consultant understands pricing-condition config (Hero Dependency) | High | Critical | Critical | Open | PgM | Pair a second resource; document config by 30 Jul | 2026-07-30 | Hero Dependency | 2
| R3 | Risk | UAT environment unstable; 40% of test cycles lost to downtime | Medium | High | High | Open | Infra Lead | Escalate to vendor; secure dedicated UAT instance | 2026-07-10 | Death By Governance
| A1 | Assumption | Business frees 6 SMEs full-time for UAT — not yet confirmed by sponsor | Medium | High | High | Open | Sponsor | Confirm SME release at next steering | 2026-07-05 | Nobody Wants To Decide
| A2 | Assumption | Legacy system stays live through hypercare (no early decommission) | Low | Medium | Low | Open | IT Director | Validate decommission date in cutover plan | 2026-08-01 | Silent Resistance
| I1 | Issue | Bank payment-gateway integration failing in SIT — 3 weeks open | High | Critical | Critical | Open | Integration Lead | Joint war-room with vendor; daily standup | 2026-07-08 | Death By Governance
| I2 | Issue | Steering has not closed chart-of-accounts decision (blocks 4 streams) | High | Critical | Critical | Open | CFO | Force decision via escalation pack | 2026-07-04 | Hero Dependency
| D1 | Dependency | GL config depends on finalised chart of accounts (see I2) | High | Critical | Critical | Open | Finance Lead | Blocked until I2 closed | 2026-07-04 | Nobody Wants To Decide
| D2 | Dependency | Cutover rehearsal depends on stable UAT (see R3) | Medium | High | High | Open | Cutover Lead | Sequenced after R3 resolved | 2026-08-15

## 3·Decision Log
DECISION LOG
Every decision has ONE named owner and a date. Aging & overdue flags auto-calculate. 'Nobody Wants To Decide' dies here.
| Decision velocity |  | 19 |  |  | Open decisions | 3 | Overdue | 0
| ID | Decision required | Owner (one name) | Raised | Needed by | Decision made | Decided on | Status | Days to close | Aging flag | PMOS Pattern | rank
| D1 | Chart of accounts structure (4-segment vs 6) | CFO | 2026-06-01 | 2026-06-20 |  |  | Open |  | DUE SOON | Nobody Wants To Decide | 1
| D2 | Single global template vs country localisation | Sponsor | 2026-06-05 | 2026-06-25 |  |  | Open |  | DUE SOON | Nobody Wants To Decide | 2
| D3 | Go / no-go criteria for cutover | Steering | 2026-06-10 | 2026-08-15 |  |  | Open |  | ON TRACK | Nobody Wants To Decide | 3
| D4 | Hypercare staffing model & duration | PgM | 2026-05-20 | 2026-06-10 | Hybrid: 4 wks onsite + 8 wks remote | 2026-06-08 | Closed | 19 | — | Hero Dependency
| D5 | Data archival policy for legacy records | IT Director | 2026-05-15 | 2026-06-05 | Archive 7 yrs, then purge | 2026-06-03 | Closed | 19 | — | Death By Governance
Formulas:
Aging flag = IF([Status]="Closed","—",IF([Needed by]="","",IF(TODAY()>[Needed by],"OVERDUE",IF(TODAY()>=[Needed by]-5,"DUE SOON","ON TRACK"))))

## 4·Recovery Actions
RECOVERY ENGINE — IMMEDIATE / 30 / 60 / 90 DAY PLAN
A phased recovery system. Each action has an owner, a dependency, a success metric, a RAG status and an expected PMOS-score improvement. Progress rolls up to the Executive Dashboard.
| Recovery score | 37.14% |  | Expected health lift | 69 | pts | Actions done | 0 / 18
| ID | Action | Owner | Dependency | Due | RAG | Success metric | Progress | Δ Health | PMOS Pattern | PHASE ROLLUP
| IMMEDIATE — first 7 days · stop the bleeding | [9 empty] | Phase | % complete | Δ health | Status
| I1 | Freeze scope; stand up a single change-control gate | PgM | Sponsor mandate | 2026-07-05 | GREEN | Zero ungoverned changes in week 1 | 100% | 3 | Death By Governance | Immediate | 85% | 6 | GREEN
| I2 | Name a backup for every single-point-of-failure person | Delivery Mgr | Hero map complete | 2026-07-06 | RED | Every critical role has 2 names | 40% | 6 | Hero Dependency | 30 days | 30% | 24 | RED
| I3 | Book the sponsor decision slot (weekly, 45 min) | PgM | Sponsor calendar | 2026-07-04 | GREEN | Slot in calendar, first one held | 100% | 4 | Nobody Wants To Decide | 60 days | 20% | 17 | RED
| I4 | Kill one recurring forum that produced no decision | PMO Lead | Governance review | 2026-07-05 | GREEN | 1 forum cancelled, capacity freed | 100% | 2 | Death By Governance | 90 days | 0% | 13 | RED
30 DAYS — stabilise · rebuild control
| D1 | Pair a 2nd resource on pricing config; document runbook | Delivery Mgr | I2 done | 2026-07-30 | RED | Runbook signed off; bus-factor ≥2 | 40% | 8 | Hero Dependency
| D2 | Cut approval chains to max 2 signatures | PMO Lead | Governance review | 2026-07-20 | AMBER | No path needs >2 sign-offs | 50% | 6 | Death By Governance
| D3 | Publish decision log; force the COA decision | CFO office | I3 done | 2026-07-12 | RED | COA decided; log live & public | 30% | 5 | Nobody Wants To Decide
| D4 | Vendor master data cleansing squad live | Data Lead | Resource approved | 2026-08-01 | RED | Duplicate rate <2% | 0% | 5 | Silent Resistance
60 DAYS — recover · prove the fix
| S1 | Dedicated UAT instance; defect closure >90% | Infra Lead | D4 underway | 2026-08-15 | AMBER | Defect closure rate >90% | 60% | 6 | Silent Resistance
| S2 | Stakeholder recovery plan for resistant teams | Change Lead | Heatmap complete | 2026-08-20 | RED | 2 resistant groups → passive/champion | 0% | 5 | Silent Resistance
| S3 | Mock cutover rehearsal #1 end-to-end | Cutover Mgr | Data migration ready | 2026-08-25 | RED | Rehearsal run; gaps logged | 0% | 6 | Hero Dependency
90 DAYS — sustain · lock in builder behaviours
| N1 | Go/no-go criteria & owner agreed and signed | Steering | S3 done | 2026-09-10 | RED | Criteria signed; owner named | 0% | 5 | Nobody Wants To Decide
| N2 | Hypercare team rostered; escalation path live | Service Owner | Vendor SLA confirmed | 2026-09-15 | RED | Roster + SLA published | 0% | 4 | Hero Dependency
| N3 | Embed weekly build session; protect what works | PgM | Culture review | 2026-09-20 | RED | Session running 4 weeks straight | 0% | 4 | Builder Culture
Δ Health = the PMOS-health points this action is expected to recover when complete. 'Expected health lift' (top) sums the points still to be earned from incomplete actions — your recovery runway.

## 5·Go-Live Readiness
GO-LIVE READINESS DASHBOARD
Five readiness domains. Each scores 0–100%. Overall readiness rolls up to the Executive Dashboard.
Readiness is a behavioral outcome, not a completion %. Score honestly.
| Readiness checkpoint | Score | Weight | Evidence / gap
DATA MIGRATION READINESS
| Master data cleansed & validated | 55% | 1
| Migration rehearsed against real volumes | 40% | 1
| Reconciliation controls signed off | 30% | 1
| → Data Migration Readiness score | 41.67%
UAT READINESS
| Test scripts cover critical business processes | 70% | 1
| Defect closure rate > 90% | 45% | 1
| Business sign-off obtained | 20% | 1
| → UAT Readiness score | 45%
TRAINING READINESS
| Role-based training delivered | 60% | 1
| Training effectiveness measured (not just attendance) | 30% | 1
| Floor-walker / support model ready | 50% | 1
| → Training Readiness score | 46.67%
CUTOVER READINESS
| Cutover plan rehearsed end-to-end | 35% | 1
| Rollback plan tested | 25% | 1
| Go/no-go criteria & owner agreed | 40% | 1
| → Cutover Readiness score | 33.33%
SUPPORT (HYPERCARE) READINESS
| Hypercare team named & rostered | 65% | 1
| Escalation path published | 70% | 1
| Known-issues log & SLAs ready | 45% | 1
| → Support (Hypercare) Readiness score | 60%
OVERALL GO-LIVE READINESS
| Weighted overall readiness | 45.33%

## 6·Stakeholder Heatmap
STAKEHOLDER HEATMAP
Map each stakeholder's stance and influence. Adoption score rolls up automatically. Target: move Resistant → Passive → Champion.
| Adoption score | 55% |  | Champions | 1 | Resistant | 2
| Stakeholder / group | Role | Influence | Current stance | Adoption % | Trend | Recovery action | PMOS Pattern
| Finance team | Process owners | High | Resistant | 35% | flat | Stakeholder recovery plan; involve in COA decision | Silent Resistance
| Warehouse ops | End users | High | Passive | 55% | up | Floor-walkers + quick-win demo | Silent Resistance
| CFO | Sponsor | High | Champion | 90% | up | Keep visible; use in steering | Hero Dependency
| Procurement | Process owners | Medium | Resistant | 40% | down | Address shadow-spreadsheet root cause | Builder Culture
| IT support | Hypercare | Medium | Passive | 60% | up | Early hypercare involvement | Nobody Wants To Decide
| Plant managers | Influencers | High | Passive | 50% | flat | 1:1 engagement; address go-live fears

## 7·Steering Pack
STEERING COMMITTEE PACK
Auto-generated from the live tabs. Refresh before each steering. Do not hand-edit the linked cells.
| Program | Project Atlas — SAP S/4HANA | 2026-06-20
1 · HEADLINE
| PMOS Health | 25
| Go-Live Readiness | 45.33%
| Recovery Score | 37.14%
| Financial Exposure | 7900254.0416
2 · TOP RISKS NEEDING THIS COMMITTEE (Critical & Open)
| ID | Risk | Owner
| R1 | Data migration: legacy vendor master has 18% duplicate records; cleansing not started | Data Lead
| R2 | Only one consultant understands pricing-condition config (Hero Dependency) | PgM
—
—
3 · DECISIONS NEEDED TODAY (Open & due)
| ID | Decision | Owner
| D1 | Chart of accounts structure (4-segment vs 6) | CFO
| D2 | Single global template vs country localisation | Sponsor
| D3 | Go / no-go criteria for cutover | Steering
—
4 · RECOVERY PROGRESS vs 30/60/90 PLAN
| Actions complete | 0 of 19
| Overall recovery | 37.14%
| Adoption score | 55%
What NOT to do: do not walk the committee through every workstream. Bring the 2–3 decisions only they can make.

## 8·Financial Exposure
FINANCIAL EXPOSURE CALCULATOR
Model the cost of doing nothing. Blue cells are your inputs; everything else calculates. Currency shown in your selected unit.
| Currency | USD | Set once — all figures below use this. INR shows Lakh/Crore.
INPUTS
| Program budget (in millions, your currency) | 15
| Weekly run-rate (% of budget burned per week) | 1.25%
| Expected delay (weeks) | 12
| Daily blended team cost (your currency) | 18000
| Extra resource days needed for recovery | 240
| Annual business benefit at stake (millions) | 6
| Benefit lost per month of delay (%) | 8%
| Recovery programme cost (your currency) | 450000
CALCULATED EXPOSURE
| Delay cost (run-rate × weeks) | 2250000
| Recovery resource cost (day-rate × days) | 4320000
| Benefit realisation impact (delay × benefit/mo) | 1330254.0416
| Recovery programme cost | 450000
| TOTAL EXPOSURE IF NOTHING CHANGES | 7900254.0416
| Recovery ROI (exposure avoided ÷ recovery cost) | 17.5561
Every 1 unit spent on recovery avoids this many in exposure.
Note: figures are in your selected currency's base units. In the PMOS web report these render with Lakh/Crore (INR) or Million/Billion (USD/GBP/EUR) automatically.

## 9·Pattern Dashboard
PMOS™ PATTERN DASHBOARD — THE BEHAVIORAL CONTROL TOWER
The five PMOS patterns are the root cause. Every risk, decision, stakeholder and recovery action traces back to one of them. This is the centre of the Command Center.
Score each pattern 0–100 from your latest diagnostic (higher = more dysfunction; Builder Culture is inverse — higher is better). Columns I–L pull live from the other tabs.
| PATTERN | W-3 | W-2 | W-1 | NOW | TREND | SEVERITY | Risks | Decisions | People | Actions | RECOMMENDED NEXT MOVE
| Hero Dependency™ | 95 | 92 | 90 | 90 | ▼ improving | CRITICAL | 1 | 0 | 1 | 4 | Pair every single-point-of-failure with a named backup now; start knowledge transfer this week.
| Death By Governance™ | 88 | 85 | 80 | 80 | ▼ improving | CRITICAL | 1 | 0 | 0 | 3 | Cut approvals to max two layers; kill one standing forum that produced no decision last month.
| Nobody Wants To Decide™ | 85 | 82 | 78 | 78 | ▼ improving | CRITICAL | 0 | 3 | 1 | 3 | Put one named owner + deadline on every open decision; escalate any decision aged >10 days.
| Silent Resistance™ | 70 | 68 | 67 | 67 | ▼ improving | ELEVATED | 1 | 0 | 2 | 3 | Run a shadow-process audit; convert two resistant stakeholders with a visible quick win.
| Builder Culture™ (↑ good) | 30 | 33 | 38 | 38 | ▲ improving | WEAK | 0 | 0 | 1 | 1 | Reinforce problem-solving wins publicly; protect the behaviours already working.
PMOS HEALTH INDEX
| Composite health (0–100) |  |  |  | 25 | ← Feeds the Executive Dashboard. Below 25 = critical behavioral failure underway.
EXPECTED HEALTH LIFT FROM THE RECOVERY PLAN
| Current composite health |  |  |  | 25 | where the program sits today
| Total Δ from open recovery actions |  |  |  | 69 | sum of expected health points across all recovery actions
| Projected health if plan delivered |  |  |  | 94 | realistic target if every recovery action lands — your recovery business case in one number
HOW TO READ THIS TAB
• Each pattern's NOW score drives its severity and links. The patterns are the root cause; the columns to the right show how much live work each one is generating.
• Risks / Decisions / People / Actions count the open items tagged to each pattern across the other tabs. A pattern with high score AND high counts is where to spend your week.
• Tag items to patterns using the 'PMOS Pattern' column on the RAID, Decision, Stakeholder and Recovery tabs. The counts here update automatically.
• The green block is your recovery business case: today's health, the lift your plan is expected to deliver, and the projected end state. Take it to your sponsor.